## Status Report
Status Report for Team 3 - Orderbook Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2020-09-21 | Overall Status: | Green
Contact: | Anmol | Explanation:
Prepared By: | Jarang
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Zeenat (Backend) | Finished logic in the back end
Buchi (Lead) | Finished linking front end to back end
Anmol(Backend) | continued cleaning up documentation
Eric (Frontend) | Worked on High level overview and wireframes
ID # | Key Issues | Action Plan |  |  | Status
1 | Validation | still working through it |  |  | in-progress
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 100%
Back-end |  | 95% | 2020-09-24
Business logic |  | 100%
Front-end |  | 95% | 2020-09-23
Testing |  | 10%
Presentation |  | 20% | 2020-09-25
Reviewing requirements |  | 100%