## Status Report
Status Report for Team 3 - Orderbook Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2020-09-23 | Overall Status: | Green
Contact: | Anmol | Explanation:
Prepared By: | Jarang
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Zeenat (Backend) | Worked on user Manual
Buchi (Lead) | Finished Validation, working on Data creation
Anmol(Backend) | worked on testing
Eric (Frontend) | Worked on Peer Review
ID # | Key Issues | Action Plan |  |  | Status
1 | Finishing up testing | still working through it |  |  | in-progress
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 100%
Back-end |  | 100% | 2020-09-24
Business logic |  | 100%
Front-end |  | 100% | 2020-09-23
Testing |  | 65%
Presentation |  | 40% | 2020-09-25
Reviewing requirements |  | 100%