## Status Report
Status Report for Team 3 - Orderbook Project
Project |  | Status: (Red/Yellow/Green)
Date: | 2020-09-15 | Overall Status: | Green
Contact: | Buchi | Explanation:
Prepared By: | Buchi
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Zeenat (Backend) | Went through logic for matching engine
Buchi (Lead) | wrote psuedo code for methods
Anmol(Backend) | Worked on flowcharts for backend
Eric (Frontend) | Worked on flowcharts for backend
ID # | Key Issues | Action Plan |  |  | Status
Critical Milestones |  | Health | Due Date | Comment/Status
Environment setup |  | 95%
Back-end |  | 10% |  | finalize backend logic
Business logic |  | 0%
Front-end |  | 8%
Testing |  | 0%
Presentation |  | 0%
Reviewing requirements |  | 100%